## ProjectSchedule
MQIS – 15-Week Project Schedule
Thapar Institute of Engineering and Technology |  | Project Start: | 2026-08-03
Bharat Bhardwaj (Project Lead) |  | Today: | 2026-09-13
|  | Display Week: | 1 |  |  | Week 1 ¦ 03 Aug – 09 Aug | [6 empty] | Week 2 ¦ 10 Aug – 16 Aug | [6 empty] | Week 3 ¦ 17 Aug – 23 Aug | [6 empty] | Week 4 ¦ 24 Aug – 30 Aug | [6 empty] | Week 5 ¦ 31 Aug – 06 Sep | [6 empty] | Week 6 ¦ 07 Sep – 13 Sep
 | time axis 2026-08-03 to 2026-09-13
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-08-03 to 2026-09-13
Bharat Bhardwaj – Detection & Integration
Week 1: Literature/tooling survey; finalize dataset | Bharat Bhardwaj | 100% | 2026-08-03 | 2026-08-09 | bar: 2026-08-03 to 2026-08-09
Week 2: Set up reference-image comparison pipeline | Bharat Bhardwaj | 100% | 2026-08-10 | 2026-08-16 | bar: 2026-08-10 to 2026-08-16
Week 3: Implement grayscale diff + thresholding | Bharat Bhardwaj | 100% | 2026-08-17 | 2026-08-23 | bar: 2026-08-17 to 2026-08-23
Week 4: Add contour extraction + bounding box | Bharat Bhardwaj | 100% | 2026-08-24 | 2026-08-30 | bar: 2026-08-24 to 2026-08-30
Week 5: Implement defect classification mapping | Bharat Bhardwaj | 100% | 2026-08-31 | 2026-09-06 | bar: 2026-08-31 to 2026-09-06
Week 6: Milestone 1: Working detection on sample dataset | Bharat Bhardwaj | 100% | 2026-09-07 | 2026-09-13 | bar: 2026-09-07 to 2026-09-13
Week 7: Tune thresholds; reduce false positives | Bharat Bhardwaj |  | 2026-09-14 | 2026-09-20
Week 8: Add severity/confidence scoring | Bharat Bhardwaj |  | 2026-09-21 | 2026-09-27
Week 9: Visual annotation (bounding box + label overlay) | Bharat Bhardwaj |  | 2026-09-28 | 2026-10-04
Week 10: Integration testing with live dashboard | Bharat Bhardwaj |  | 2026-10-05 | 2026-10-11
Week 11: Milestone 2: Full inspection view working | Bharat Bhardwaj |  | 2026-10-12 | 2026-10-18
Week 12: End-to-end integration (all modules combined) | Bharat Bhardwaj |  | 2026-10-19 | 2026-10-25
Week 13: System testing: run ≥50 inspections, log accuracy | Bharat Bhardwaj |  | 2026-10-26 | 2026-11-01
Week 14: Bug fixing; buffer week for unresolved issues | Bharat Bhardwaj |  | 2026-11-02 | 2026-11-08
Week 15: Final demo prep, documentation, presentation | Bharat Bhardwaj |  | 2026-11-09 | 2026-11-15
Rishit – Data & Analytics
Week 1: Define DB schema for event logging | Rishit | 100% | 2026-08-03 | 2026-08-09 | bar: 2026-08-03 to 2026-08-09
Week 2: Implement database.py (init, log, query) | Rishit | 100% | 2026-08-10 | 2026-08-16 | bar: 2026-08-10 to 2026-08-16
Week 3: Test DB read/write with dummy data | Rishit | 100% | 2026-08-17 | 2026-08-23 | bar: 2026-08-17 to 2026-08-23
Week 4: Build minimal Streamlit shell (app.py skeleton) | Rishit | 100% | 2026-08-24 | 2026-08-30 | bar: 2026-08-24 to 2026-08-30
Week 5: Wire detection output into DB logging | Rishit | 100% | 2026-08-31 | 2026-09-06 | bar: 2026-08-31 to 2026-09-06
Week 6: Milestone 1: Logging pipeline integrated | Rishit | 100% | 2026-09-07 | 2026-09-13 | bar: 2026-09-07 to 2026-09-13
Week 7: Build analytics.py: rejection rate, by-line summary | Rishit |  | 2026-09-14 | 2026-09-20
Week 8: Add by-type and by-hour breakdowns | Rishit |  | 2026-09-21 | 2026-09-27
Week 9: Add line-status flags (Normal/Warning/Critical) | Rishit |  | 2026-09-28 | 2026-10-04
Week 10: Live stats panel in Streamlit (metrics, bar chart) | Rishit |  | 2026-10-05 | 2026-10-11
Week 11: Milestone 2: Full analytics panel working | Rishit |  | 2026-10-12 | 2026-10-18
Week 12: End-to-end integration (all modules combined) | Rishit |  | 2026-10-19 | 2026-10-25
Week 13: Validate analytics against manual ground truth | Rishit |  | 2026-10-26 | 2026-11-01
Week 14: Bug fixing; buffer week for unresolved issues | Rishit |  | 2026-11-02 | 2026-11-08
Week 15: Final demo prep, documentation, presentation | Rishit |  | 2026-11-09 | 2026-11-15
Asmita – RAG & Reporting
Week 1: Survey RAG stack (Chroma, embeddings, Ollama) | Asmita | 100% | 2026-08-03 | 2026-08-09 | bar: 2026-08-03 to 2026-08-09
Week 2: Set up local Llama 3.2 via Ollama; test basic chat call | Asmita | 100% | 2026-08-10 | 2026-08-16 | bar: 2026-08-10 to 2026-08-16
Week 3: Draft initial factory knowledge base (.txt notes) | Asmita | 100% | 2026-08-17 | 2026-08-23 | bar: 2026-08-17 to 2026-08-23
Week 4: Implement embedding pipeline for knowledge base | Asmita | 100% | 2026-08-24 | 2026-08-30 | bar: 2026-08-24 to 2026-08-30
Week 5: Implement Chroma collection build/query | Asmita | 100% | 2026-08-31 | 2026-09-06 | bar: 2026-08-31 to 2026-09-06
Week 6: Milestone 1: Retrieval returns relevant chunks | Asmita | 100% | 2026-09-07 | 2026-09-13 | bar: 2026-09-07 to 2026-09-13
Week 7: Draft prompt template for shift report generation | Asmita |  | 2026-09-14 | 2026-09-20
Week 8: Implement generate_report() end-to-end | Asmita |  | 2026-09-21 | 2026-09-27
Week 9: Implement answer_question() for free-text queries | Asmita |  | 2026-09-28 | 2026-10-04
Week 10: Integrate AI assistant panel into dashboard UI | Asmita |  | 2026-10-05 | 2026-10-11
Week 11: Milestone 2: Full RAG panel working | Asmita |  | 2026-10-12 | 2026-10-18
Week 12: End-to-end integration (all modules combined) | Asmita |  | 2026-10-19 | 2026-10-25
Week 13: Evaluate report quality/latency against target | Asmita |  | 2026-10-26 | 2026-11-01
Week 14: Bug fixing; buffer week for unresolved issues | Asmita |  | 2026-11-02 | 2026-11-08
Week 15: Final demo prep, documentation, presentation | Asmita |  | 2026-11-09 | 2026-11-15
Legend: | Completed | Planned | Today
SIMPLE GANTT CHART by Vertex42.com
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
MQIS Gantt Chart populated using the Contract Playbook template design.
Visible project timeline: 03-Aug-2026 through 13-Sep-2026.
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.